## FAT Plan
EQUIPMENT INSTALLATION TRACKING
Document Number: | DO737348 |  | Revision: | 1 |  | FAT SPECIMEN SHIPPING ADDRESS
Customer Name: | Polymer Chemistry Innovations |  | Author: |  |  | ZwickRoell GmbH & Co. KG
Install Location: | Polymer Chemistry Innovations / 4231 South Fremont Avenue / Tucson, AZ 85714 / USA |  | Approval Date: |  |  | Wareneingang-Service
Last Updated: |  |  | Approved By: |  |  | Lämmerweg 28
89079 Ulm Germany
INSTRUCTIONS & LEGEND | [5 empty] | Attn: Heiko Haller
Status Codes: | Not Started = Task pending ¦ In Progress = Currently active ¦ Completed = Finished ¦ Blocked = Issue preventing progress ¦ On Hold = Temporarily paused
Phase Codes: | Pre-FAT = Preparation activities ¦ FAT = Factory Acceptance Test ¦ Logistics = Shipping & handling ¦ Install = On-site installation ¦ Qualification = IQOQ/UL/CSA
KEY CONTACTS | [5 empty] | PROJECT PROGRESS
Role | Name | Company | Phone | Email |  | Metric | Count
Regional Sales Manager (RSM) | [5 empty] | Total Tasks:
Project Manager | Eric Milan | ZwickRoell, US | 678-650-2716 | eric.milan@zwickroell.com |  | Completed:
Tech Support | TBD |  |  |  |  | In Progress:
Field Service Engineer (FSE) | [5 empty] | Blocked:
Industry Manager (IM) | James Ritchey | ZwickRoell, US | 781-927-4023 | james.ritchey@zwickroell.com |  | % Complete:
ZRU Project Manager | Heiko Haller | ZwickRoell Ulm | +49 7305 10 11809 | heiko.haller@zwickroell.com
Customer Contact | Porter, Katie | Polymer Chemistry Innovations | +1(520)808-5695 | katie@polychemistry.com
Logistics Coordinator | Anita Boyd | ZwickRoell, US | 678-695-5752 | anita.boyd@zwickroell.com
MILESTONE TRACKING
Phase | Target Date | Actual Date | Activity Description | Responsible Party | Status | Dependencies | Comments / Meeting Notes | Document References
Pre-FAT |  |  | Confirm order from ZRU to ZNRA: Get confirming order to XXX with FAT & delivery expectations | Project Manager | Not Started | — |  | Purchase Order
Pre-FAT |  |  | Plan initial call to review FAT & initial Logistics Plan w/ZRNA Team & Customer • Provide schematic with dimensions • Confirm physical delivery path to laboratory • Third party riggers if needed • Review facilities requirements • Plan cadence meetings | Tech Support, RSM, IM, Project Manager, Customer | Not Started | Task 1 | Power: 120V (standard plugs) Compressed Air: min 6.5 bar/95 psi Regulator & filter on air line Air line connector: ¼" female NPTs ZwickRoell supplies 6mm flex hose | Logistics Plan
Pre-FAT |  |  | Confirm FAT details • Dates confirmed • Review of FAT process & details • FAT specimens provided at least 3-4 weeks in advance of FAT | Tech Support, RSM, IM, Project Manager, Customer | Not Started | Task 2 |  | FAT Protocol, IQOQ Docs
Pre-FAT |  |  | Confirm FAT & Installation documentation • FAT protocol provided by customer • Manual provided by ZwickRoell • IQOQ documents provided by ZwickRoell for finalization | Tech Support, RSM, IM, Project Manager, Customer | Not Started | Task 3
Pre-FAT |  |  | Confirm Installation Details • Dates confirmed by ZNRA • Review facilities & confirm details overview • Review schedule/timeline • Status update on FAT specimens • Review FAT protocol documents • Review IQOQ documents • Confirm logistics & facilities needs • Review install dates & requirements • Verify specimens available for install | Tech Support, RSM, IM, Project Manager, Customer | Not Started | Task 4
FAT |  |  | Confirm Travel Planning • Attendee list (names & title) • Proposed travel dates • ZNRA travel guide supplied • Proposed dinner schedule | Tech Support, RSM, IM, Project Manager, Customer | Not Started | Task 5 |  | Travel Itinerary
FAT |  |  | FAT Execution in Ulm | Customer, FSE, ZRU PM | Not Started | Task 6 |  | FAT Report
Logistics |  |  | Shipment of system | Anita Boyd | Not Started | Task 7 |  | Shipping Documents
Install |  |  | Installation at Customer Location | FSE | Not Started | Task 8 |  | Installation Report
Qualification |  |  | IQOQ Execution | FSE, Customer | Not Started | Task 9 |  | IQOQ Protocol
Qualification |  |  | Training & Handover | FSE, Customer | Not Started | Task 10 |  | Training Materials
Qualification |  |  | Final Sign-Off & Project Closure | Project Manager, Customer | Not Started | Task 11 |  | Sign-Off Form
RISK & ISSUES LOG
Issue # | Date Identified | Description | Impact (H/M/L) | Owner | Status | • Delay > 5 business days on critical path
ISS-001 |  |  |  |  | Open | • Customer-reported blocking issue
ISS-002 |  |  |  |  | Open | • Safety or compliance concern identified
ISS-003 |  |  |  |  | Open | • Resource unavailability impacting schedule
• Budget variance > 10%
Escalation Contact: [Manager Name]
SIGN-OFF & APPROVAL
Role | Name | Signature | Date | Comments
Customer Representative
Project Manager
Field Service Engineer
Quality Assurance
FACILITIES REQUIREMENTS CHECKLIST
Item | Requirement | Customer Confirms | Verified By | Date Verified
Power Supply | 120V (standard plugs) | ☐
Compressed Air | Minimum 6.5 bar / 95 psi | ☐
Air Regulator | Regulator & filter on air line | ☐
Air Connector | ¼" female NPTs | ☐
Floor Space | Per schematic requirements | ☐
Delivery Path | Clear path to laboratory | ☐
Rigging Access | Third-party rigger coordination | ☐
Network/IT | Per equipment requirements | ☐